## 1Q
ITEM | PROJECT | TASK | TIMELINE | [15 empty] | TARGET | RESULT | OVERALL % ACCOMP
|  |  | DECEMBER |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | Month-
|  |  | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | Week
1 | Warehouse Inventory System | Creating Dashboard and Upload UI | [17 empty] | Complete | 100% | bar: DECEMBER WK1
|  | Creating Database and Upload Function for 2 different CSV File | [17 empty] | Complete | 100% | bar: DECEMBER WK1 to DECEMBER WK3
|  | Adding Datatable UI and it's Functions | [17 empty] | Complete | 100% | bar: DECEMBER WK2 to DECEMBER WK4
|  | Enhancing UI Design and Creating Export Function | [17 empty] | Complete | 100% | bar: DECEMBER WK3
|  | Adding Search by Date Function | [17 empty] | Complete | 100% | bar: DECEMBER WK4
|  | Creating Validation for User Inputs | [17 empty] | Almost done | 90% | bar: DECEMBER WK1 to DECEMBER WK2; DECEMBER WK4 to JANUARY WK1
|  | Creating Login and Register UI | [17 empty] | Complete | 100% | bar: DECEMBER WK4 to JANUARY WK1
|  | Creating functionality for Login and Register | [17 empty] | No Password Reset Functionality | 80% | bar: DECEMBER WK4 to JANUARY WK1
|  | Enhancing UI Design on Login, Register and Upload | [17 empty] | Complete | 100% | bar: JANUARY WK1 to JANUARY WK2
|  | Creating delete function if upload data is already in 1 month | [17 empty] | Complete | 100% | bar: JANUARY WK2
|  | Testing and Debugging | [17 empty] | complete | 100% | bar: DECEMBER WK4 to JANUARY WK2
100%
| Regular Tasks | Innoland Website support | [18 empty] | 100%
|  | Citrineland Website support | [18 empty] | 100%
|  | TheMedian | [18 empty] | 100%
|  | Intranet Update ISO & Forms | [18 empty] | 100%

## 2Q
ITEM | PROJECT | TASK | TIMELINE | [11 empty] | TARGET | RESULT | OVERALL % ACCOMP
|  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  | Month-
|  |  | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | Week
100%
100%
100%
100%
80%
| Regular Tasks | Innoland Website support | [14 empty] | 100%
|  | Citrineland Website support | [14 empty] | 100%
|  | TheMedian | [14 empty] | 100%
|  | Intranet Update ISO & Forms | [14 empty] | 100%

## 3Q
ITEM | PROJECT | TASK | TIMELINE | [11 empty] | TARGET | RESULT | OVERALL % ACCOMP
|  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | Month-
|  |  | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | Week
100%
100%
100%
90%
100%
100%
100%
70%
30%
90%
100%
100%
| Regular Tasks | Innoland Website support | [14 empty] | 100%
|  | Citrineland Website support | [14 empty] | 100%
|  | TheMedian | [14 empty] | 100%
|  | Intranet Update ISO & Forms | [14 empty] | 100%

## 4Q
ITEM | PROJECT | TASK | TIMELINE | [11 empty] | TARGET | RESULT | OVERALL % ACCOMP
|  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | Month-
|  |  | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | Week
85%
100%
100%
25%
| Regular Tasks | Innoland Website support | [14 empty] | 100%
|  | Citrineland Website support | [14 empty] | 100%
|  | TheMedian | [14 empty] | 100%
|  | Intranet Update ISO & Forms | [14 empty] | 100%